## 1
| Actor name | Actors Weight | UC title | Transactions | UC Weight | Factor | Description | Weight | Rating (0-5) | TF (W*R) | Effort Computation | [5 empty] | Lookup tables
1 | Unregistered Citizen | 3 | Consult interactive map/summary table | 2 | 5 | T1 | Distributed System | 2 | 5 | 10 | [6 empty] | Productivity Norms |  | Actor weights | Ratings
2 | Citizen | 3 | View report | 3 | 5 | T2 | Response time | 2 | 2 | 4
3 | Organization Office Staff | 3 | Receive report updates | 4 | 10 | T3 | End User Efficiency | 1 | 4 | 4 | Context factors |  |  | Productivity norms |  |  | PN1 | 10 | 1 | 0
4 | Technical Office Staff | 3 | Register in the system | 5 | 10 | T4 | Complex Internal Processing | 1 | 1 | 1 | [6 empty] | PN2 | 14 | 2 | 0.5
5 | External company personnel | 3 | View public statistics | 3 | 5 | T5 | Reusable Code | 1 | 4 | 4 | T Factor | 48 |  | n1 | 1 |  | PN3 | 18 | 3 | 1
6 | Message gateway | 1 | Fill in a problem form | 7 | 10 | T6 | Easy to install | 0.5 | 5 | 2.5 | TCF | 1.08 |  | n2 | 0 |  |  |  |  | 1.5
7 | Email gateway | 1 | Reply to message | 3 | 5 | T7 | Easy to use | 0.5 | 1 | 0.5 |  |  |  | n1+n2 | 1 |  |  |  |  | 2
8 | External chatbot | 1 | View private statistics | 3 | 5 | T8 | Cross-platform support | 2 | 5 | 10 | E Factor | 21 | [7 empty] | 2.5
9 | Report gateway | 1 | Accept/Reject reports | 3 | 5 | T9 | Easy to change | 1 | 2 | 2 | ECF | 0.77 |  | Productivity | 10 | PH / UCP |  |  |  | 3
10 |  |  | Assigns report to the Technical Office responsible | 3 | 5 | T10 | Concurrent | 1 | 5 | 5 | [9 empty] | 3.5
11 |  |  | Send message to the citizen | 3 | 5 | T11 | Includes Security Features | 1 | 1 | 1 | UUCP | 119 | [7 empty] | 4
12 |  |  | Write an explanation for rejected reports | 3 | 5 | T12 | Provides Access for 3rd parties | 1 | 3 | 3 | UCP | 98.9604 | [7 empty] | 4.5
13 |  |  | Plan intervention | 3 | 5 | T13 | User Training Required | 1 | 1 | 1 | [9 empty] | 5
14 |  |  | Evaluate further "Suspended" reports | 3 | 5 | [5 empty] | Effort | 989.604 | person hours
15 |  |  | Update status and close report | 3 | 5 | [6 empty] | equivalent to
16 |  |  | Change report status | 3 | 5 | Factor | Description | Weight | Rating (0-5) | EF (W*R) |  | 123.7005 | person days
17 |  |  | Exchange information/comments | 3 | 5 | F1 | Familiarity With Project Domain | 1.5 | 3 | 4.5
18 | [5 empty] | F2 | Application Experience | 0.5 | 0 | 0 | Person cost | 450 | €/day
19 | [5 empty] | F3 | Object Oriented Experience | 1 | 4 | 4
20 | [5 empty] | F4 | Lead Analyst Capability | 0.5 | 5 | 2.5
21 | [5 empty] | F5 | Motivation | 1 | 4 | 4
22 | [5 empty] | F6 | Stable requirements | 2 | 4 | 8
23 | [5 empty] | F7 | Part Time Workers | -1 | 1 | -1
24 | [5 empty] | F8 | Difficulty of programming language | -1 | 1 | -1
[11 empty] | Total cost | 55665.225

## 2
| Actor name | Actors Weight | UC title | Transactions | UC Weight | Factor | Description | Weight | Rating (0-5) | TF (W*R) | Effort Computation | [5 empty] | Lookup tables
1 | Unregistered Citizen | 3 | Consult interactive map/summary table | 2 | 5 | T1 | Distributed System | 2 | 5 | 10 | [6 empty] | Productivity Norms |  | Actor weights | Ratings
2 | Citizen | 3 | View report | 3 | 5 | T2 | Response time | 2 | 2 | 4
3 | Organization Office Staff | 3 | Receive report updates | 4 | 10 | T3 | End User Efficiency | 1 | 4 | 4 | Context factors |  |  | Productivity norms |  |  | PN1 | 10 | 1 | 0
4 | Technical Office Staff | 3 | Register in the system | 5 | 10 | T4 | Complex Internal Processing | 1 | 1 | 1 | [6 empty] | PN2 | 14 | 2 | 0.5
5 | External company personnel | 3 | View public statistics | 3 | 5 | T5 | Reusable Code | 1 | 4 | 4 | T Factor | 48 |  | n1 | 3 |  | PN3 | 18 | 3 | 1
6 | Message gateway | 1 | Fill in a problem form | 7 | 10 | T6 | Easy to install | 0.5 | 5 | 2.5 | TCF | 1.08 |  | n2 | 0 |  |  |  |  | 1.5
7 | Email gateway | 1 | Reply to message | 3 | 5 | T7 | Easy to use | 0.5 | 1 | 0.5 |  |  |  | n1+n2 | 3 |  |  |  |  | 2
8 | External chatbot | 1 | View private statistics | 3 | 5 | T8 | Cross-platform support | 2 | 5 | 10 | E Factor | 16 | [7 empty] | 2.5
9 | Report gateway | 1 | Accept/Reject reports | 3 | 5 | T9 | Easy to change | 1 | 2 | 2 | ECF | 0.92 |  | Productivity | 14 | PH / UCP |  |  |  | 3
10 |  |  | Assigns report to the Technical Office responsible | 3 | 5 | T10 | Concurrent | 1 | 5 | 5 | [9 empty] | 3.5
11 |  |  | Send message to the citizen | 3 | 5 | T11 | Includes Security Features | 1 | 1 | 1 | UUCP | 119 | [7 empty] | 4
12 |  |  | Write an explanation for rejected reports | 3 | 5 | T12 | Provides Access for 3rd parties | 1 | 3 | 3 | UCP | 118.2384 | [7 empty] | 4.5
13 |  |  | Plan intervention | 3 | 5 | T13 | User Training Required | 1 | 1 | 1 | [9 empty] | 5
14 |  |  | Evaluate further "Suspended" reports | 3 | 5 | [5 empty] | Effort | 1655.3376 | person hours
15 |  |  | Update status and close report | 3 | 5 | [6 empty] | equivalent to
16 |  |  | Change report status | 3 | 5 | Factor | Description | Weight | Rating (0-5) | EF (W*R) |  | 206.9172 | person days
17 |  |  | Exchange information/comments | 3 | 5 | F1 | Familiarity With Project Domain | 1.5 | 5 | 7.5
18 | [5 empty] | F2 | Application Experience | 0.5 | 0 | 0 | Person cost | 200 | €/day
19 | [5 empty] | F3 | Object Oriented Experience | 1 | 5 | 5
20 | [5 empty] | F4 | Lead Analyst Capability | 0.5 | 5 | 2.5
21 | [5 empty] | F5 | Motivation | 1 | 2 | 2
22 | [5 empty] | F6 | Stable requirements | 2 | 1 | 2
23 | [5 empty] | F7 | Part Time Workers | -1 | 2 | -2
24 | [5 empty] | F8 | Difficulty of programming language | -1 | 1 | -1
[11 empty] | Total cost | 41383.44